## SID Risk Register
[18 empty] | Project Name: |  |  |  | Author:
[6 empty] | Safety By Design Risk Assessment Register | [11 empty] | Job No: |  |  |  | Approved By:
[18 empty] | Stage of Design: |  |  |  | Date:
[6 empty] | At Each State of the Design Process, Think of Ways to Reduce the Risks | [11 empty] | (Note: minimum of 2 reviews per project - 1 for each design phase) |  |  |  | Revision:
RISKS ASSOCIATED WITH DESIGN ELEMENTS | [10 empty] | EXISTING RISK CONTROLS |  |  |  |  | ADDITIONAL CORRECTIVE ACTIONS | [5 empty] | RESIDUAL RISK
Ref | Date Raised | Systemic Failure Categories | Hazard (Guideword) | Project Phase | Top Risk Event | Top Risk Event Cause | Top Risk Event Impact | Raw Systemic Risk Rating |  |  | Existing controls, if any | Existing Control Type | Controlled Risk Rating |  |  | Proposed Corrective Actions | Proposed Corrective Action Type | Corrective Action Design Status | Corrective Action Accepted? (Y/N) | Corrective Action Owner | Date of Acceptance | Residual Risk Details | Residual Risk Rating |  |  | Residual Risk Owner
|  | Systemic Failure Categories | [5 empty] | Likelihood | Impact | Risk Rating |  |  | Likelihood | Impact | Risk Rating | [7 empty] | Likelihood | Impact | Risk Rating
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
[5 empty] | Consequences | 1) Low 2) Moderate 3) Significant 4) Major 5) Critical | [6 empty] | Hazards / risks considered are those that are project / site specific, non-standard / bespoke designs, special processes, high hazard risks (e.g. non ‘business as usual’ hazards) that have been identified at the time of the review(s). Other risks will continue to appear during the design life of the project and should be assessed and managed by appropriate parties.
[5 empty] | Likelihood | 1) Rare 2) Unlikely 3) Possible 4) Likely 5) Almost Certain
[5 empty] | Level of Risk: | L) Low M) Medium H) High E) Extreme
Note on C6: Systemic failures are the unintended consequences generated by the confluence of hazard classes and the systemic failure categories within a complex system, rather than the result of a specific, individual or isolated factor.
Note on D6: A source or situation with the potential for injury or harm, property or environmental damage, or a combination of these.
Note on E6: What project phase will the risk impact?
Note on F6: The point where there is no longer any satisfactory control over the hazard that leads to the hazard manifesting itself in a harmful manner. Also known as the first undesired or hazardous event.
Note on G6: Determine the events and conditions that most directly lead to the potential top events.
Note on H6: Detail the impact or consequences to people or the environment.
Note on L6: What existing controls are in place to eliminate or minimise the systemic health and safety risks?
Note on Q6: Apply the hierarchy of hazard controls throughout design phases to eliminate or minimise the systemic health and safety risks;
Note on S6: Record the ‘why’ and ‘how’ decisions made during the continuum of a project’s planning, design, construction and post-construction phases; and Record what the outcomes of the decisions were.
Note on W6: Remaining systemic health and safety risks after identified systemic health and safety risks are eliminated or mitigated.
Note on I7: How likely is it that the event will occur, if there are no controls are in place?
Note on J7: What is the impact of the event, if there are no controls are in place?
Note on K7: This is the uncontrolled risk rating.
Note on N7: How likely is it that the event will occur, if the existing controls are in place?
Note on O7: What is the impact of the event, if the existing controls are in place?
Note on P7: This is the controlled risk rating.
Note on X7: How likely is it that the event will occur, if the corrective actions are completed?
Note on Y7: What is the impact of the event, if the corrective actions are completed?
Note on Z7: This is the residual risk rating.

## Blank SID Hazard Sheet (hidden)
Project Name: |  | DPT Dry Dock Crane | This sheet can be used before the first workshop to allow designers to come to the workshop with some hazards already identified
RISKS ASSOCIATED WITH DESIGN ELEMENTS
Ref | Hazard (Guideword) | Cause / Outcome
1 | Design Phase
1.01
1.02
2 | Construction Phase
2.01
2.02
2.03
2.04
2.05
2.06
2.07
2.08
2.09
2.1
3 | Operation Phase
3.01
3.02
3.03
3.04
3.05
4 | Maintenance Phase
4.01
4.02
4.03
4.04
4.05
5 | Demolition Phase
5.01
5.02
5.03
5.04
5.05
5.06
5.07
5.08

## Guide Words
Safety In Design - Suggested Guide Words
The following hazard guide words will help you analyse each element of your design scope. Take each element of your design and run through the guide words to identify hazards introduced by the design and any related pre-existing hazard sources (e.g. local environment or site conditions). Consider the Construction, Maintenance, Operation and Demolition of the element being assessed and how this connects in with other elements of the overall design.
Category | Definition
Environment | The circumstances, objects or conditions surrounding the proposed building or facility, including factors such as terrain, climate, soil, living things, waterways, that affect the proposed building or facility. Also includes the internal environment of the building or facility.
Management | Processes involving the managing workers or machines necessary to accomplish desired goals and objects.
Materials | The materials used to make a thing. In the context of a building or facility, it refers to the building materials that planned or used to construct it.
Personnel | People employed in organisation or engaged in an organised undertaking to undertake specific tasks
Task | The actions required to achieve a specific objective.
Hazard Guidewords | Prompts
Biological | • Airborne fibres/particulates e.g. Asbestos • Bacteria • Blood-borne pathogens • Contaminated soil • Contaminated water • Fungi/mould • Hygiene concerns • Insect/animal bites or stings • Vapours/dust/fumes/exhausts • Viruses • Water immersion
Biomechanical | • Body position, uncomfortable position • Eye strain • Muscular over exertion/manual handling • Repetitive operations • Working posture
Chemical | • Chemical transfer activities • Contamination dust, chemicals, sediment, effluent, non-segregated waste • Corrosives • Depleted oxygen • Explosives • Flammable vapours/materials • Gasses (Oxygen, Carbon, Monoxide/Dioxide/Hydrogen Sulphide/Ammonia) • Piping/tanks containing chemicals • Potential for trapped gases (pocket of gas) • Pyrophoric materials (ignites in Oxygen) • Toxic gases/carcinogens • Unapproved chemical
Ecological | • Equipment dropped to water • Soil contamination • Spill/chemical to water • Windblown litter
Electrical | • Compressors and transformer • Exposed energised systems • Lighting and batteries • Overhead power lines • Portable electrical equipment • Static electricity • Underground/buried electrical cables • Unguarded or exposed electrical equipment
Gravity | • Anchor point/lifting equipment (chains/slings/harness) • Cave-in • Converging/sloping/slippery surfaces • Fall from height/climbing • Inadequate/restricted entry and exit • Moving/dropped/falling objects • Roof/walking/platform/handrails • Scaffolding/elevated work platform/roof collapse • Shifting loads/materials • Structural collapse (incl. adjacent) • Suspended in harness • Uneven ground/same level fall
Mechanical | • Equipment failure (brakes, lights, pumps, valves and tools) • Equipment under tension e.g. springs • Exposed drive belts/conveyors • Exposed rotating machinery/rollers/screw conveyors
Motion | • Aircraft transportation • Anchoring/deck lines/ropes • Congested work area • Ejected debris/tool parts • Equipment/crane overloading • Excavation equipment • Foreign body in eye • Line of fire & pinch points - hands/fingers/feet/legs • Line of fire - body position shifting and swinging loads • Marine vessel transportation • Moving vehicles/plant • Road conditions • Vehicle/plant turnover • Water ingress
Noise | • Equipment noise e.g. grinding, shipping, engines • High-pressure release • Impact noise • Sirens and alarms
Pressure | • Cylinders/tanks/vessels • Exposed piping • Hoses • Pneumatic/hydraulic • Underground piping
Psychosocial | • Aggression/violence • Bullying/harassment • Heavy workload • Human factors (fatigue, lapses in focus) • Lone worker • Low resource/inadequate skills • Monotonous tasks • Poor communications • Stress • Unpleasant tasks
Radiation | • Ionising - X-Ray (sources) • Ionising - lasers • Ionising - radon • Non-ionising - radio frequency and microwaves • Non-ionising - crack detection equipment • Non-ionising - lasers • Non-ionising - power lines • Non-ionising - radiant heat • Non-ionising - UV e.g. sun, lighting, water treatment • Non-ionising - welding arc
Temprature | • Cooking and heating appliances • Exposure to extreme weather conditions (wind, fog, rain) • Flammable/combustible material (incl. vegetation) • Friction (ignition source) • Hot/cold surfaces • Ignition sources (process/tools/vehicles) • Steam • Thermal discomfort
Vibration | • Whole body vibration • Hand/arm vibration
Responsibility of the Designer
Understand | Construction hazards, Range of use activities, Operational and Maintenance requirements
Identify | Hazards and risks noted above
Communicate | To client risks and alternative options
Duties of the Designer
Refer | To appropriate codes and standards, legislation
Document | Meetings, letters, archives etc
Inform others | Contractors, users, replacement staff
Project Phases
Design
Construction
Operational
Maintenance
Demolition

## Risk Evaluation
Safety In Design - Definitions |  |  |  |  | Safety In Design - Risk Magnitudes
Consequence and Likelihood Scales |  |  |  |  | The following requirements set out the level of participation in the organisation required for management of the risk outcomes
Identified risks are evaluated in terms of the severity of the consequence and the likelihood of an event should they occur. These definitions and score are shown below |  |  |  |  | LOW | Low Level risks can be accepted by the Project Manager
C = Consequences |  | Score | Description |  |  | In most cases risks at this level are unlikely to require further action to be undertaken . Where further action is required this is to be monitored by the Project Manger or appropriate delegated person
Minor |  | 1 | No Medical Treatment |  | MEDIUM | Medium level risks can be accepted by the Project Manager where the risk has been identified
Moderate |  | 2 | Minor injury requiring medical treatment but <1 week LTI, or |  |  | Where relevant solutions to reduce the risk level should be developed . These are to be monitored by the Project Director until completed
|  |  | Reversible Disability |  | HIGH | High level risks must be brought to the attention of the client project manager
Major |  | 3 | Single fatality, or |  |  | All controlled risks assessed as high shall be discussed with the client to agree mitigation and reported to the stakeholders
|  |  | Severe irreversible disability (>30%) to one or more persons |  |  | Where relevant solutions to reduce the risk level should be developed .These are to be monitored by the Project Manager/ Project Director until completed
Extreme |  | 4 | Multiple fatalities, or |  | EXTREME | Extreme level risks must be notified to senior levels in both Beca and the client
|  |  | Significant irreversible disability to >10 persons |  |  | All controlled risks assessed as extreme shall be notified immediately to the senior management of all stakeholders
L = Likelihood |  | Score | Description |  |  | Where relevant solutions to reduce the risk level should be developed .These are to be monitored and reported monthly until completed
Rare |  | 1 | May only occur in exceptional circumstances
<1% probability during construction OR
Occurs less frequently than once every 50 years during operation
Unlikely |  | 2 | Could infrequently occur
1-10% probability during construction OR
Occurs at least once per 10-50 years during operation
Possible |  | 3 | May occur at occasionally
10-20% probability during construction OR
Occurs at least once per 5-10 years during operation
Likely |  | 4 | Will commonly occur in most circumstances
20-50% probability during construction ,OR
Occurs at least once per 1-5 years during operation
Almost Certain |  | 5 | Is expected to occur in most circumstances
>50% probability during construction, OR
Occurs at least once every year during operation
LR = LEVELS OF RISK
The following matrix is then used to determine the appropriate magnitude for each risk
Likelihood (L) | Impact ( I )
| Minor | Moderate | Major | Extreme
Almost Certain | MEDIUM | HIGH | VERY HIGH | VERY HIGH
Likely | LOW | HIGH | VERY HIGH | VERY HIGH
Possible | LOW | MEDIUM | HIGH | VERY HIGH
Unlikely | LOW | MEDIUM | MEDIUM | HIGH
Rare | LOW | LOW | MEDIUM | HIGH
Hierarchy of Hazards - Controls
Controls | Details
Elimination | Elimination is the most effective control measure, it involves eliminating the hazard and its associated risk/s. If you cannot eliminate the hazard, eliminate as many of the associated risk/s.
Substitution (Minimisation) | Substitute the hazard with something safer. This may not remove all the hazards associated with the process or activity any may introduce different hazards, but the overall harm or health effects will be lessened.
Isolation (Minimisation) | Isolate the hazard by physically separating the source of harm from people by distance or barrier, including time barriers. For example, restrict contact with plant and equipment, reduce exposure time, lock hazardous chemicals away and only us them under strict conditions.
Engineering (Minimisation) | Look for technological solutions that reduce risk, e.g. use machines to do work that would be hazardous to humans, or use more modern plant with in-built safety features.
Administration (Minimisation) | Develop and document safe methods of work (safe work procedures, safe work method statements) and provide appropriate training, instruction and information to reduce the potential for harm.
PPE (Minimisation) | Personal protective equipment (PPE) reduces workers' exposure to the hazard. PPE includes saftey gloves, protective eyewear, earmuffs, hard hats, aprons, saftey footwear and dust masks.

## Example SID Risk Register (hidden)
|  |  |  | Design Risk Assessment Register | [6 empty] | Author (Role): |  |  |  | Job No:
[11 empty] | Approved By: |  |  |  | Date
[7 empty] | Project Name: |  |  |  | Revision: |  |  |  | Stage of Design / Project:
(Note: minimum of 2 reviews per project)
| RISKS ASSOCIATED WITH DESIGN ELEMENTS |  |  |  |  | Risk Matrix |  | PROPOSED & APPROVED MITIGATION MEASURES | Mitigated Risk & Resolution | [6 empty] | RESIDUAL RISK
Ref | Hazard (Guideword) | Cause / Outcome | Existing Controls, If Any | L | C | LR | Risk Owner | Proposed Control (1 Eliminate, 2 Substitute, 3 Reduce, 4 Control) | L | C | LR | Client Approved | Design Status | Date | Risk Owner | Action Required
1 | Construction
1.01 | Heights / Depths | Steep pitched roof could result in personnel falling during installation |  | 5 | 4 | #REF! | RS (Arch) | Review design and minimise pitch as much as possible. | 5 | 3 | H | Yes | CLOSED |  | Contractor | Contractor to provide specialist scaffolding to roof areas and coordinate installation system.
1.02 | Egress / Access | Lack of access space, or ease of access, for large plant (Chiller, MSB, Transformer, Cooling Towers) could result in non-standard or risky installation procedures resulting in injury. |  | 3 | 3 | M | MB (Bldg Serv.) | Review design layouts and provide sufficient access space | 3 | 1 | L | Yes | CLOSED |  | Contractor | Contractor to consider installation process.
1.03
1.04
2 | Operation
2.01 | Utilities/Services | High noise levels from main plant (chillers, medical air compressors, fans) to adjacent occupied spaces could result in unacceptable background noise. |  | 2 | 4 | M | RS (Arch) | Obtain acoustic advise from acoustic consultant to treat plant rooms. | 2 | 1 | L | Yes | CLOSED |  | - | -
2.02
2.03
2.04
3 | Maintenance
3.01 | Heights / Depths | Falling could occur during maintenance of external rooftop louvres on top of 4 storey high link bridge. |  | 5 | 3 | H | RS (Arch) | Safety line to be provided | 5 | 1 | M | Yes | CLOSED |  | Client | Process for trained staff with appropriate safety gear only to access the roof area.
3.02
3.03
3.04
4 | Demolition
4.01
Key; | [7 empty] | Notes: | Hazards / risks considered are those that are project / site specific, non-standard / bespoke designs, special processes, high hazard risks (e.g. non ‘business as usual’ hazards) that have been identified at the time of the review(s). Other risks will continue to appear during the design life of the project and should be assessed and managed by appropriate parties.
C= | Consequence | 1) Low 2) Moderate 3) Significant 4) Major 5) Critical | 1) Low 2) Moderate 3) Significant 4) Major 5) Critical |  | LR = | Level of Risk: |  | L) Low M) Medium H) High E) Extreme
L= | Likelihood | 1) Rare 2) Unlikely 3) Possible 4) Likely 5) Almost Certain | 1) Rare 2) Unlikely 3) Possible 4) Likely 5) Almost Certain
Note on F6: Likelihood: How likely is the hazard to occur?
Note on G6: Consequence: What is the most likely consequence of the hazard
Note on H6: Level of Risk: See 'tables' tab for matrix of levels of risk
Note on L6: Likelihood: How likely is the hazard to occur?
Note on M6: Consequence: What is the most likely consequence of the hazard
Note on N6: Level of Risk: See 'tables' tab for matrix of levels of risk

## VLookup (hidden)
Likelihood | Consequence | Rank
1 | 1 | L |  | 1 | 2 | 3 | 4 | 5
1 | 2 | L | 1 | L | L | M | M | H
1 | 3 | M | 2 | L | L | M | H | H
1 | 4 | M | 3 | L | M | H | H | E
1 | 5 | H | 4 | M | M | H | E | E
2 | 1 | L | 5 | M | H | H | E | E
2 | 2 | L
2 | 3 | M
2 | 4 | H
2 | 5 | H
3 | 1 | L
3 | 2 | M
3 | 3 | H
3 | 4 | H
3 | 5 | E
4 | 1 | M
4 | 2 | M
4 | 3 | H
4 | 4 | E
4 | 5 | E
5 | 1 | M
5 | 2 | H
5 | 3 | H
5 | 4 | E
5 | 5 | E

## SID Risk Register (2) (hidden)
Safety in Design Risk Assessment Register - (Project Name) Reviewed: (Date)
|  |  |  | Risk Matrix |  |  | PROPOSED & APPROVED MITIGATION MEASURES | Mitigated Risk & Resolution | [6 empty] | RESIDUAL RISK
Ref | Risk Description | Cause & Outcome | Existing controls, if any | L | C | LR | Proposed Control (1 Eliminate, 2 Substitute, 3 Reduce, 4 Control) | L | C | LR | Risk Owner (For the Phase, Record name of risk owner - the person who can mitigate / control this risk) | Client Approved | Design Status (Design Phase & Draft / Final) | Date (Date for completion of the proposed control to be actioned) | Risk Owner | Action Required / Notes
1 | Design Phase
1.1 | Staging / tie in of Old to New System | - Poor planning and execution of the Staging / tie-in of the old system with the new system. (i.e. fire protection systems, or site access) Outcome: Loss of SH road use, loss of water supply of Camp or village - loss of military operation; Time and cost to mitigate. | NA | 3 | 4 | H | - Review design to provide required level of service during system staging and transition from old to new. (Kristi Whyte) - Prepare staging plan, coordination with NZDF and other projects/maintenance (Rob Ansell) | 3 | 2 | M | Person's Name (not a team or group or entity) | (Design Lead to confirm with NZDF through SG process) | Detailed Design (Draft) | (Date)
1.2 | Disposal of material | - Exposure to contaminants when handing soil during ground investigations and site visits. Outcome: Harm / Illness to persons, in the short or long term. - Contamination is different to expected and cannot be removed from site - type or location. Outcome: Additional costs and programme delays to look for alternative material disposal options. | - Inform workers and personnel in area of the contamination. NZDF management processes in place. - Avoid contaminated areas for routing of pipework in the design, ongoing on site checks, use of NZDF contamination records / information. | 4 | 3 | H | - Speak with Ross Winters at Beca and Adam Gray regarding the Contaminated material management plan developed to transfer lessons / learning that can be included in design phase. (Kristi Whyte) - Construction Phase - Brief contractor of hazards and NZDF material management requirements | 3 | 3 | H | Person's Name (not a team or group or entity) | (Design Lead to confirm with NZDF through SG process) |  | (Date) |  | SID risk transferred to risk register
2 | Construction Phase
2.1 | Significant rainfall /storm events during construction works | - Major storm event during construction of the new assets. Outcome: River flooding work site / pumpstation / pipe trenching works; delays to programme; costs to recover storm damage and recommence works; potential loss of water supply to users. | - Use of existing infrastructure (that has a level of known resilience). | 3 | 3 | H | - Review fish passage design for resilience during flood event. (Kristi Whyte) - Procurement contract to outline requirement for some kind of flood management during construction controls. (Rob Ansell) - Construction method statements to address base and flood water flows. (Contractor) - Works to be postponed during flood events. (Contractor) - Sediment Erosion Control Plans. (Contractor) | 3 | 2 | M | Person's Name (not a team or group or entity) | (Design Lead to confirm with NZDF through SG process) |  | (Date)
2.2 | Trench collapse | - Excavations/trenches not adequately supported (i.e. shoring/shielding). Outcome: Trench collapse on people working in trench - Injury or death. | - Trench depth over 1.5m requires shielding / support Design. Asset depth to be limited so far as is reasonably practicable in the design stage. - Ground investigation ground structure / soil type information to inform Design for wet or dry conditions. | 4 | 4 | E | - Install adequate trench support system where required; allowing for site specific soil and groundwater conditions. - Use of Thrust blocks. (Contractor) - Ground water monitoring (Contractor) - Construction monitoring - spotter. | 2 | 3 | M | Person's Name (not a team or group or entity) | (Design Lead to confirm with NZDF through SG process) |  | (Date)
2.3 | Slips, trips and falls | Slips, trips and falls resulting from uneven ground and other construction works hazards. | NA | 4 | 3 | H | Contractor to keep a tidy site, provide safe access to works areas and ensure surfaces affected by the works are maintained and made safe throughout construction. Surfaces to be reinstated adequately upon completion. | 2 | 3 | M | Person's Name (not a team or group or entity) | (Design Lead to confirm with NZDF through SG process) |  | (Date)
2.4 | Pressure testing | Failure of pipe during pressure testing, resulting in trench/surface flooding | NA | 3 | 3 | H | Follow standard procedures for pressure testing (AS 2566, water care etc) Safe proximity to pipeline/clear zone maintained during testing along with notification to public that testing is being conducted. | 2 | 2 | L | Person's Name (not a team or group or entity) | (Design Lead to confirm with NZDF through SG process) |  | (Date)
2.5 | Hygiene Testing for Commissioning System. | - Failure to chlorine or dichlorination of water main prior to commissioning. Outcome: Contaminated water supply, illness. Cost and reputation impacts; delays to system start up re restart process. | - Chlorine flushing at treatment plant facility. | 2 | 3 | M | - Consider level of disinfection required (noting raw water pipe line). If required, follow standard procedures for disinfecting pipes. Check if consent is required to discharge chlorinated water. (Kristi Whyte) - Review design for risks of cross-contamination at system cut-over process. (Kristi Whyte) - Debris flushing of lines during construction EG: plastic shavings or fuel contaminants from construction activity (Contractor) - Prepare Cleaning Requirements Process Plan for commission and transition to new system, including chemical flushing requirements. (Kristi Whyte); (then NZDF / Contractor) - Post construction back flushing of lines. (Contractor) | 2 | 2 | L | Person's Name (not a team or group or entity) | (Design Lead to confirm with NZDF through SG process) |  | (Date)
2.6 | Moving Vehicles / Plant strike | Moving vehicles / plant on site during construction. Outcome: Injury or death to persons in vicinity of incident; loss of critical services to camp or village; Stop work - programme delays, investigations & prosecutions. | NA | 3 | 4 | H | - Prepare traffic management plan. (Contractor) - Dedicated pedestrian walkways should be established - consider for requirements in procurement contract. (Rob Ansell) -Camp communications regarding construction activity and "off limits areas". (Rob Ansell) | 2 | 3 | M | Person's Name (not a team or group or entity) | (Design Lead to confirm with NZDF through SG process) |  | (Date)
2.7 | Covid-19 | - Covid / pandemic or other flu type sickness event. Outcome: Personnel and providers unwell & unable to work to progress project. Time and cost lost with delays; escalation of materials. | - Government and NZDF guidance throughout different alert levels. - NZDF Covid controls, vaccinations & hygiene controls. | 3 | 2 | M | - All parties to follow the latest Ministry of Health guidelines, including social distancing, increased hand washing and infectious disease protocols as necessary at the time. - Early contractor procurement - to confirm supplier; and materials ordering at start of project to secure. | 2 | 3 | M | Person's Name (not a team or group or entity) | (Design Lead to confirm with NZDF through SG process) |  | (Date) |  | SID risk transferred to risk register
2.8 | Utilities Service Strike - Underground / Overhead | - Known or unknown services (including gas or fuel lines) may be struck during ground investigation or construction activity. Outcome: Injury or death to persons in vicinity of incident; loss of critical services to camp or village; Stop work - programme delays, investigations & prosecutions. | - Existing GIS data provided to design team. - Ground investigation prechecks. | 3 | 3 | H | - Designer to provide key plan / high risk areas. Comms and Power important on base (Kristi Whyte) - Follow standard practice for service location prior to excavation (to be address in contract spec). - Construction GPR & hydrovacing requirement. (Contractor) | 2 | 3 | M | Person's Name (not a team or group or entity) | (Design Lead to confirm with NZDF through SG process) |  | (Date)
2.9 | Hot Works - Butt welding | - High temperature welding in close proximity to high risk areas / assets or other personnel. Outcome: Injury or death to persons in vicinity of incident; loss of critical services to camp or village (Fire); Stop work - programme delays, investigations & prosecutions. | NA | 2 | 4 | H | - Include methodology and health and safety plan requirements in contract docs. Plus liaise with mil fire - hot works permit. - Contractor to follow standard hotworks procedure, and CHESS processes. | 2 | 3 | M | Person's Name (not a team or group or entity) | (Design Lead to confirm with NZDF through SG process) | Detailed Design | (Date)
2.10 | Stream Crossing Structure | - Working near the river and stream crossing areas. Outcome: Injury or death to persons working in river area - including ground investigations, site inspections / survey & construction, and defence personnel. | - NZDF CHESS. - Waitangi Stream - designed for "drill under stream" approach & use of small bridge on site. | 2 | 4 | H | - Review design for Safety in Design treatments to reduce construction hazards. (Kristi Whyte) - Environmental - review design with Planner - confirm consent requirements (Kristi Whyte) - Contractor construction methodology to consider the risks and constraints. (Contractor) | 2 | 3 | M | Person's Name (not a team or group or entity) | (Design Lead to confirm with NZDF through SG process) | Detailed Design | (Date)
2.11 | Unexploded ordinance | - Explosion of ordinance while working on site. Outcome: Injury or death to workers or other personnel in the vicinity. | - Inform workers and personnel in area of the known ordinance issues - NZDF management processes in place. - CHESS processes. - Contractor briefings. | 2 | 5 | H | - Provide known hazard areas, to be included on Designs , with disclaimers (Kristi Whyte / Rob Ansell) - Follow standard NZDF protocols communicated during contractor briefings. (NZDF - CHESS Briefing) - Contractor site controls management plan. (Contractor) | 2 | 3 | M | Person's Name (not a team or group or entity) | (Design Lead to confirm with NZDF through SG process) | Detailed Design | (Date) |  | SID risk transferred to risk register
3 | Operational Phase
3.1 | Valve Failure | The value isolating the system fails. Outcome: Not able isolate parts of the network for critical maintenance or emergency response; loss of critical services to camp and village. | NA | 4 | 1 | M | Clair NZDF to continues comms with iwi | 1 | 2 | L |  | (Design Lead to confirm with NZDF through SG process) |  | (Date)
3.2 | Pipeline Rupture | - Water system pipe bursts. Outcome: loss of water pressure in systems, system shutdown to repair; loss of critical supply to camp and village users. | - Regular inspection and maintenance programme. - Flow metering will highlight rupture / loss of flow early warning. - Valves to isolate. - Reservoir condition assessment to allow for reservoirs to be operational and buffer the flow. | 3 | 2 | M |  | 1 | 2 | L |  | (Design Lead to confirm with NZDF through SG process) |  | (Date)
3.3 | Silt in pipe / pumps | - Silting material in the pipelines or at Dam face (build-up of material) Outcome: Loss of supply to users; additional costs to maintain; fish passage impacts | - Notches in structure. - Mesh box to filter water and protect fish protection. - Climbing structure for fish. | 3 | 2 | M | - Consider additional scour locations in the design to add additional silting mitigation. | 2 | 1 | L |  | (Design Lead to confirm with NZDF through SG process) |  | (Date)
3.4 | Volcanic Ash Contamination | - Volcanic Eruption ash affects water source and supply infrastructure. Outcome: Water sources contaminated with ash; ash affects water abstraction & treatment - no clean water supply for camp and village. | - NZDF Volcanic Response plan. -Regular maintenance programme - removal of silt / ash / material from behind Dam area. - Self cleaning systems. - Note - as at August 2002, status is Quiet. | 3 | 5 | E | - Revisit design to understand any safety equipment such as hand rails etc. (Kristi Whyte) - NZDF to investigation desire for an alternative (ground water bore) source of water. | 3 | 5 | E |  | (Design Lead to confirm with NZDF through SG process) |  | (Date) | Rob Ansell | SID risk transferred to risk register
4 | Maintenance Phase
4.1 | Silt Screening of Dam Area | - Maintenance activity to manage silt screening in the "working near water" area. Outcome: Injury or death from unsafe location to carry out maintenance activity (loss of footing etc); Stop work investigations and reputational impacts; delays and costs. | - Old handrails on dams to assist with personnel safety during inspections & maintenance activity. - Self cleaning systems - reducing on site requirement. | 3 | 4 | H | - Design upgrade to handrail, and any other safety requirements - eg tethering points , barriers etc. (Kristi Whyte) - Operations/Contractors to wear suitable PPE. (Contractor) | 3 | 2 | M |  | (Design Lead to confirm with NZDF through SG process) |  | (Date)
4.2 | Service Strike on New Pipe (2015 State Highway line) | - Damage to 2015 pipeline during construction works in area. Outcome: Injury or death to persons in vicinity of incident; loss of critical services to camp or village; Interruption to State Highway; Stop work - programme delays, investigations & prosecutions. | - Existing GIS data provided to design team. - Ground investigation prechecks. | 3 | 3 | H | - Designer to provide key plan / high risk areas. (Kristi Whyte) - Follow standard practice for service location prior to excavation (to be address in contract spec). - Construction GPR & hydrovacing requirement. (Contractor) | 2 | 3 | M |  | (Design Lead to confirm with NZDF through SG process) |  | (Date)
| Consequences | 1) Low 2) Moderate 3) Significant 4) Major 5) Critical |  | Hazards / risks considered are those that are project / site specific, non-standard / bespoke designs, special processes, high hazard risks (e.g. non ‘business as usual’ hazards) that have been identified at the time of the review(s). Other risks will continue to appear during the design life of the project and should be assessed and managed by appropriate parties.
| Likelihood | 1) Rare 2) Unlikely 3) Possible 4) Likely 5) Almost Certain
| Level of Risk: | L) Low M) Medium H) High E) Extreme
Note on F6: Likelihood: How likely is the hazard to occur?
Note on G6: Consequence: What is the most likely consequence of the hazard
Note on H6: Level of Risk: See 'tables' tab for matrix of levels of risk
Note on K6: Likelihood: How likely is the hazard to occur?
Note on L6: Consequence: What is the most likely consequence of the hazard
Note on M6: Level of Risk: See 'tables' tab for matrix of levels of risk